## Sheet1
{{Title}}
项目名称 |  | 项目分类、状态及所属区域 | [6 empty] | 合同额 （元） | 有效合同额(除税) | 剩余 合同额 （元） | 主要工程量概况说明 | 工程量完成情况（方） | [6 empty] | 产值完成情况（元，含增值税） | [10 empty] | 进度结算及合同收款情况（元，含增值税） | [5 empty] | 进度偏差主因 |  | 标后预算执行分析（含增值税） | [13 empty] | 成本偏差主因 |  | 实施单位 （四字以内简称） |  | 投入人员 |  | 业主单位名称 | 新签合同乙方名称 | 甲方单位 | 项目负责人及联系方式 |  | 报表负责人及联系方式 |  | 一级行业分类代码 | 一级行业分类 | 二级行业分类代码 | 二级行业分类 | 三级行业分类代码 | 三级行业分类 | 项目编码 | 支付滞后比例(%)
[13 empty] | 月度完成情况 |  |  | 年度累计完成情况 |  |  | 累计 完成工程量 | 月度完成情况 |  |  |  |  | 年度累计完成情况 |  |  |  | 累计 完成产值 | 累计 外包支出 | 进度结算情况(甲方确认产值) |  |  | 合同收款情况(甲方付款金额) |  |  |  |  | 标后预算 毛利率 （%） | 未编制 标后预算原因 | 计划完成 编制时间 | 月度完成情况 |  |  | 年度累计完成情况 |  |  | 累计完成情况 |  |  | 实际 毛利率 （%） | 毛利率 偏差 （%）
| 填报月份 | 业务分类 | 现汇 投资 | 在建 完工 | 所属 区域 | 省域 国别 | 所属 区市 | 施工资质 |  |  |  |  | 本月 计划工程量 | 本月 完成工程量 | 本月 进度偏差 | 年度 计划工程量 | 年度 完成工程量 | 年度 进度偏差 |  | 本月 计划产值 | 本月 完成产值 | 本月 进度偏差 | 本月外包支出 | 主要形象进度描述 | 年度 计划产值 | 年度 完成产值 | 年度 进度偏差 | 年度 外包支出 |  |  | 本月 | 本年 | 累计 | 本月 | 本年 | 累计 | 主要 原因 | 偏差原因简述 |  |  |  | 本月 预计成本 | 本月 完成成本 | 本月 成本偏差 | 年度 预计成本 | 年度 完成成本 | 年度 成本偏差 | 标后预算 预计成本 | 项目累计 完成成本 | 标后预算 成本偏差 |  |  | 主要 原因 | 偏差原因简述 | 二级单位 | 三级单位 | 管理人员 （人） | 施工人员 （人） |  |  |  | 负责人 | 联系方式 | 负责人 | 联系方式
[9 empty] | M |  | M-E |  | A | B | A-B | C | D | C-D | E | A | B | A-B |  |  | C | D | C-D |  | E | [7 empty] | 甲方原因 |  | G | 简述 | 年-月-日 | a | b | a-b | c | d | c-d | e=E（1-G) | f | e-f | g | g-G | 甲方原因
{{MonthtreportData.Name}} | {{MonthtreportData.StrMonthTime}} | {{MonthtreportData.ProjectType}} | {{MonthtreportData.Label}} | {{MonthtreportData.State}} | {{MonthtreportData.Area}} | {{MonthtreportData.Nationality}} | {{MonthtreportData.District}} | {{MonthtreportData.Construction}} | {{MonthtreportData.ContractAmount}} | {{MonthtreportData.ValidContractAmount}} | {{MonthtreportData.ResidueContractAmount}} | {{MonthtreportData.Remarks}} | {{MonthtreportData.PlanQuantities}} | {{MonthtreportData.AccomplishQuantities}} | {{MonthtreportData.DeviationQuantities}} | {{MonthtreportData.YearPlanQuantities}} | {{MonthtreportData.YearAccomplishQuantities}} | {{MonthtreportData.YearDeviation}} | {{MonthtreportData.AccumulativeQuantities}} | {{MonthtreportData.PlanOutPutValue}} | {{MonthtreportData.AccomplishValue}} | {{MonthtreportData.ScheduleOutPutValue}} | {{MonthtreportData.OutsourcingExpensesAmount}} | {{MonthtreportData.ProgressDescription}} | {{MonthtreportData.YearPlanOutPutValue}} | {{MonthtreportData.YearAccomplishValue}} | {{MonthtreportData.YearAnnualOutputValue}} | {{MonthtreportData.YearOutsourcingExpensesAmount}} | {{MonthtreportData.CumulativeCompleted}} | {{MonthtreportData.CumulativeOutsourcingExpensesAmount}} | {{MonthtreportData.RecognizedValue}} | {{MonthtreportData.YearRecognizedValue}} | {{MonthtreportData.CumulativeValue}} | {{MonthtreportData.PaymentAmount}} | {{MonthtreportData.YearPaymentAmount}} | {{MonthtreportData.CumulativePaymentAmount}} | {{MonthtreportData.ProgressDeviationReason}} | {{MonthtreportData.ProgressDeviationDescription}} | {{MonthtreportData.BudgetInterestRate}} | {{MonthtreportData.BudgetaryReasons}} | {{MonthtreportData.CompilationTime}} | {{MonthtreportData.ProjectedCost}} | {{MonthtreportData.AccomplishCost}} | {{MonthtreportData.CostDeviation}} | {{MonthtreportData.YearProjectedCost}} | {{MonthtreportData.YearAccomplishCost}} | {{MonthtreportData.YearCostDeviation}} | {{MonthtreportData.PostmarkProjectedCost}} | {{MonthtreportData.CumulativeAccomplishCost}} | {{MonthtreportData.PostmarkCostDeviation}} | {{MonthtreportData.EffectiveGrossMargin}} | {{MonthtreportData.GrossMarginDeviation}} | {{MonthtreportData.CostDeviationReason}} | {{MonthtreportData.CostDeviationDescription}} | {{MonthtreportData.TweUnit}} | {{MonthtreportData.ThreeUnit}} | {{MonthtreportData.AdministrationNumber}} | {{MonthtreportData.ConstructionNumber}} | {{MonthtreportData.OwnerUnitName}} | {{MonthtreportData.SecondPartyName}} | {{MonthtreportData.FirstPartyUnit}} | {{MonthtreportData.PersonAdministration}} | {{MonthtreportData.PhoneAdministration}} | {{MonthtreportData.PersonReportForms}} | {{MonthtreportData.PhoneReportForms}} | {{MonthtreportData.OneCode}} | {{MonthtreportData.OneClassify}} | {{MonthtreportData.TweCode}} | {{MonthtreportData.TweClassify}} | {{MonthtreportData.ThreeCode}} | {{MonthtreportData.ThreeClassify}} | {{MonthtreportData.Code}} | {{MonthtreportData.PaymentLagRatio}}